## Music Recommendation Project
AI WAVE CAPSTONE PROJECT- MUSIC RECOMMENDATION ENGINE
ID | Task Name | Assigned | Anticipated Start | Anticipated End | Status | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15
1 | Development Web Application | Harshit & Shreya | 2022-10-13 | 2022-11-03 | In Progress
1.1 | Home Page | Harshit & Shreya | 2022-10-13 | 2022-10-20 | In Progress
1.2 | Login Page | Harshit & Shreya | 2022-10-13 | 2022-10-20 | In Progress
1.2.1 | User Login Home Page | Harshit & Shreya | 2022-10-13 | 2022-10-20 | In Progress
1.3 | Sign-up Page | Harshit & Shreya | 2022-10-21 | 2022-10-27 | Not Started
1.3.1 | User Registration Page | Harshit & Shreya | 2022-10-21 | 2022-10-27 | Not Started
1.3.2 | New Registered User Sign-in Page | Harshit & Shreya | 2022-10-21 | 2022-10-27 | Not Started
1.3.3 | Genre Pages | Harshit & Shreya | 2022-10-28 | 2022-11-02 | Not Started
1.4 | Web Application QA (Minimum Viable Product) | All Team Members | 2022-11-02 | 2022-11-02 | Not Started
2 | EDA | Niharika & Pushkal | 2022-10-20 | 2022-11-10 | Not Started
2.1 | Data Pre-Processing | Niharika & Pushkal | 2022-10-20 | 2022-10-27 | Not Started
2.3 | Data Normalization | Niharika & Pushkal | 2022-10-28 | 2022-11-04 | Not Started
2.4 | Data Viz. | Niharika & Pushkal | 2022-11-05 | 2022-11-10 | Not Started
3 | Implementation of AI | Niharika & Pushkal | 2022-11-10 | 2022-11-24 | Not Started
3.1 | Model-1 - Random Forest Classifier | Niharika & Pushkal | 2022-11-10 | 2022-11-17 | Not Started
3.2 | Model-2 SVM | Niharika & Pushkal | 2022-11-10 | 2022-11-17 | Not Started
3.3 | Model 3- XgBoost | Niharika & Pushkal | 2022-11-18 | 2022-11-24 | Not Started
3.4 | Model Evaluation | Niharika & Pushkal | 2022-11-18 | 2022-11-24 | Not Started
3.5 | Model Testing on Web Applications & Model Finalization (Minimum Marketable Product) | Niharika & Pushkal | 2022-11-18 | 2022-11-24 | Not Started
4 | Integration of Finalized AI Algorithm with Web Application | All Team Members | 2022-11-25 | 2022-12-02 | Not Started
4.1 | Verifying Recommendation Engine (QA & UAT) | All Team Members | 2022-12-03 | 2022-12-07 | Not Started
5 | Product Ready to Launch (Demo) | All Team Members | 2022-12-08 | 2022-12-08 | Not Started
6 | Project Presentation | All Team Members | 2022-12-08 | 2022-12-15 | Not Started
Milestones